## Sheet1
Morgan Schaffer Site Security Issues
| Details | Resolution | Status | Hours | Status | Remarks
1 | http://morganschaffer.com/ ms-admin/filemanager /file_manager.php | Remove file | Done | 0.25 | Uploaded
2 | https://morganschaffer.com needs to be redirected for now to the regular http:// site | Add a rewrite condition to htaccess to redirect domain without 'www' to the regular domain | Done | 2 | Uploaded
3 | SSL layer | Redirect normal http to https once SSL layer has been activated. 1.Add a rewrite condition on htaccess to redirect url with http to https. | Pending | 4 | Uploaded | Additonal man hours due to HTTPS broken links which generates from HTTP links.
4 | Admin users can login on the homepage | Disable admin usertypes ability to login from the homepage | Done | 4 | Uploaded
5 | Session tokens need to be added so that login is checked multiple times. | 1. Upon user logged in, create a session token 2. Save session token 3. Verify token to every pages, if false, destory all sessions to logout user and redirect to login. 4. Destory token on logout | Pending | 12 | Completed | testing ongoing
6 | http://www.morganschaffer.com/ flash.html | Remove file | Done | 0.25 | Uploaded
7 | Housekeeping: Unused files removal | 1. Delete unecessary or unused files on the server. 2. Most of the files used on every pages are saved on the database. 3. Uploaded files from the cms are always saved to the database,. We can delete uploaded files not found on the database. | Pending | 24 | Ongoing
8 | Captcha to all forms | Add captchas to all forms across the site. | Pending | 8
9 | Using Administrative access to database | 1. Create a new user without full administrative access to the database 2. Apply the new user to config or database connection file as user credentials for the database access. | Pending | 6 | Uploaded
10 | Create a 404 page | To redirect not found pages or invalid links to 404 rather than redirecting to homepage. | Pending | 4 | Uploaded
11 | Disable download of files to unlogged users | 1. Lock the directory of all downloadable files, so nobody can access these files directly. 2. Create a download script page. 2. Only allow a download script to access the directory of downloadable files. 3. The downlod script cannot be accessed be any users without login in. | Pending | 8 | Pending
12 | User access to secure directories and files. | Disallow users to access secure directories. 1. add deny to all to accesssecure file or directory | Pending | 6 | Completed | for testing
13 | Admin access to allowed IP only | If this is applicable to the client, we can allow specific user(s) IP to access the admin. |  |  | Pending | For follow up on admin users IP
14 | Testing and debugging. |  |  | 8
86.5