|  |  |  |  |
| --- | --- | --- | --- |
| **Task\_Name** | **Duration** | **Start\_Date** | **Finish\_Date** |
| **EBID Cross Browser Compatiblity** | 44 days | 6-Oct-14 | 4-Dec-14 |
| **EBID Development** | 30 days | 6-Oct-14 | 14-Nov-14 |
| Common Pages | 8 days | 6-Oct-14 | 15-Oct-14 |
| Vendor Pages | 9 days | 10-Oct-14 | 22-Oct-14 |
| Buyer Pages | 5 days | 20-Oct-14 | 24-Oct-14 |
| Purchasing Officer Pages | 3 days | 27-Oct-14 | 29-Oct-14 |
| BOC Pages | 6 days | 30-Oct-14 | 6-Nov-14 |
| BAC Pages | 6 days | 5-Nov-14 | 12-Nov-14 |
| Admin Pages | 4 days | 11-Nov-14 | 14-Nov-14 |
| **Testing** | 10 days | 13-Nov-14 | 26-Nov-14 |
| EBID Pages Testing | 10 days | 13-Nov-14 | 26-Nov-14 |
| EBID Admin Pages Testing | 5 days | 17-Nov-14 | 21-Nov-14 |
| **Production** | 9 days | 24-Nov-14 | 4-Dec-14 |
| Setup/Installation | 2 days | 24-Nov-14 | 25-Nov-14 |
| Implementation | 1 day | 4-Dec-14 | 4-Dec-14 |
|  |  |  |  |
| **Task\_Name** | **Duration** | **Start\_Date** | **Finish\_Date** |
| **AVAP Enhancement** | 55 days | 8-Dec-14 | 20-Feb-15 |
| **AVAP Development** | 52 days | 13-Oct-14 | 17-Feb-15 |
| Score Computation | 5 days | 13-Oct-14 | 17-Oct-14 |
| Rearrangement of attachment of fields | 9 days | 20-Oct-14 | 30-Oct-14 |
| Search Vendor | 6 days | 31-Oct-14 | 7-Nov-14 |
| Approved LOI with AVAP status |  |  | cancelled |
| Additonal view for VM |  |  | tentative |
| Exclude weekends (Sat & Sun) in no. of days computation (SLA) | 2 days | 10-Nov-14 | 11-Nov-14 |
| Report Management | 8 days | 12-Nov-14 | 21-Nov-14 |
| Change Password | 3 days | 24-Nov-14 | 25-Nov-14 |
| Able to reverse action taken by approver | 7 days | 26-Nov-14 | 2-Dec-14 |
| Clarification to DNB | 12 days | 3-Dec-14 | 18-Dec-14 |
| Others:   * History of vendor renewal including Recommendations by VMhead & PVMD * File attachments 20Mb each | 5 days | 19-Dec-14 | 29-Dec-14 |
|  |  |  |  |
| **Production** | 3 days | 5-Jan-15 | 7-Jan-15 |
| Setup/Installation | 2 days | 8-Jan-15 | 9-Jan-15 |
| Implementation | 1 day | 12-Jan-15 | 12-Jan-15 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Task\_Name** | **Duration** | **Start\_Date** | **Finish\_Date** |
| **AVAP Additional** | Man days |  |  |
| Admin will able to Add/Edit/Delete All email notification that AVAP sent. | 8 days |  |  |
| Admin will able to Add/Edit/Delete information in the AVAP landing page | 5 days |  |  |
| VM Head will able to select accreditation renewal by Date/Month/Year not only for 6months/1Year/2Years | 1 day |  |  |
| Approval letter to be send to vendor will reflect the actual date has been set by VMHead | 1 day |  |  |
|  | 15 days |  |  |